## summary
				2019					2020					2021					2022
Activity	Aim	Progress	Start Date	End Date	4	5	6	7	8	9	10	11	12	1	2	3	4	5	6	7	8	9	10	11	12	1	2	3	4	5	6	7	8	9	10	11	12	1	2	3
Define thesis topic		Complete	01/04/19	10/09/19
Research reading		Ongoing	01/04/19	31/03/22
(Leave of Absence)		Complete	11/06/20	18/10/20
Develop classifier	1a	90%	11/09/19	30/12/20
Obtain & pre-process TCGA experiment data	1b	Complete	11/09/19	30/06/20
Obtain& pre-process PMCC TCL data	1c	Underway	01/04/20	31/03/21
Perform Image experiments with TCGA WSI data	1d	Complete	01/03/20	31/09/2020
Perform RNA-Seq experiments with TCGA WSI data	1e	Complete	01/06/20	31/09/2020
Perform Dual-mode experiments on TCGA cancer data	2	Not Started	15//12/30	31/04/2021
Perform Dual-mode experiments on PMCC TCL data	3	Not Started	01/04/21	31/07/21
Write and submit thesis		15%	01/07/19	01/12/21
		Complete
		Underway but not complete
		Not yet started

## detail
				1	2	3	4	5	6	7	8	9	10	11	12	13	14	15	16	17	18	19	20	21	22	23	24	25	26	27	28	29	30	31	32	33	34	35	1	2	3	4	5	6	7	8	9	10	11	12	13	14	15	16	17	18	19	20	21	22	23	24	25	26	27	28	29	30	31	32	33	34	35

				2020			2021					2022
Activity	Progress	Start	End	Dec			Jan				Feb				Mar					Apr				May				Jun					Jul				Aug				Sep					Oct			Nov	Nov			Dec	Dec					Jan				Feb				Mar					Apr				May				Jun					Jul				Aug					Sep				Oct				Nov					Dec
Develop Experiment System	Complete	01/02/20	30/12/20
Extensions for Clustering	Complete	01/01/21	05/05/21
Further Testing and Code Tidy Up	Underway	01/05/21	01/08/21
Evaluation Metrics Selection	Not Started
System Evaluation	Not Started	01/08/21	31/12/21
Literature review	Not Started	20/05/21	28/02/22
Chapter Headings finalised	Underway	01/08/21	01/08/21
Write thesis (First Draft)	Not Started	01/06/21	01/12/21
Write thesis (Final Draft)	Not Started	01/12/21	28/02/22
3rd Party Reviews	Not Started	01/03/22	31/05/22
Submit	Not Started	01/06/22	01/06/22