## summary
				2019					2020					2021					2022
Activity	Aim	Progress	Start Date	End Date	4	5	6	7	8	9	10	11	12	1	2	3	4	5	6	7	8	9	10	11	12	1	2	3	4	5	6	7	8	9	10	11	12	1	2	3
Define thesis topic		Complete	01/04/19	10/09/19
Research reading		Ongoing	01/04/19	31/03/22
(Leave of Absence)		Complete	11/06/20	18/10/20
Develop classifier	1a	90%	11/09/19	30/12/20
Obtain & pre-process TCGA experiment data	1b	Complete	11/09/19	30/06/20
Obtain& pre-process PMCC TCL data	1c	Underway	01/04/20	31/03/21
Perform Image experiments with TCGA WSI data	1d	Complete	01/03/20	31/09/2020
Perform RNA-Seq experiments with TCGA WSI data	1e	Complete	01/06/20	31/09/2020
Perform Dual-mode experiments on TCGA cancer data	2	Not Started	15//12/30	31/04/2021
Perform Dual-mode experiments on PMCC TCL data	3	Not Started	01/04/21	31/07/21
Write and submit thesis		15%	01/07/19	01/12/21
		Complete
		Underway but not complete
		Not yet started

## detail
				2020			2021					2022
				Dec			Jan				Feb				Mar					Apr				May				Jun					Jul
Activity	Aim	Progress	Start Date	End Date	50	51	52	1	2	3	4	5	6	7	8	9	10	11	12	13	14	15	16	17	18	19	20	21	22	23	24	25	26	27	28	29	30	31	32	33	34	35	36	37	38	39	40	41	42	43	44	45	46	47	48	49	50	51	52	1	2	3	4	5	6	7	8	9	10	11	12	13	14	15	16	17	18	19	20	21	22	23	24	25	26	27	28	29	30	31	32	33	34	35	36	37	38	39	40	41	42	43	44	45	46	47	48	49	50	51	52
Acquire and pre-process STAD examples from GDC	1	Complete	01/02/20	30/12/20
Develop ‘minimum viable’ multimode classifier	1	Complete	11/09/19	30/12/20
Develop autoencoder version of classifier	1	95%	01/06/19	30/12/20
mod to allow all samples to be used for unimode training (rather than just matched samples)	1
Unimode and multimode experiment runs (STAD)	2
Discuss/sanity check results with pathologist (James)	2
Change bar chart so that it shows the correct score classification rather than classification with the highest score	1
Generate bar chart for rna-seq (at the moment bar chart only generated for images)	1
option to produce confusion matrix for every test example when in test mode	1
mod to gdc_fecth to make stop/start fetch of NIH data easier	2
mod to gdc_fecth to identify matched examples prior to download	2
Acquire and pre-process THYM examples from GDC	2
Unimode and multimode experiment runs (THYM)	2
Discuss/sanity check results with pathologist (James)	2
Develop unsupervised clustering capability (iff time)	4
Develop unsupervised clustering capability (iff time)	4
Acquire and pre-process THYM examples from PMCC	3	Underway	01/04/20	31/03/21
Unimode and multimode experiment runs (TCL)	3	Not Started
Reading & Seminars		50%	01/07/19	01/12/21
Write and submit thesis		15%	01/07/19	01/12/21

		Complete
		Underway
		Not yet started